## Bid Form
Developer: | Kondor Builders |  |  | Date:
Address: | 23412 Moulton Pkwy |  |  | Contact: | Pavan Hemantrao Patil
City: | Laguna Hills CA 92653 |  |  | Phone: | (626) 657-8594
|  |  |  | Email: | bids@kondorbuilders.com
PROJECT | 1249 N. GOWER ST |  |  | PLANS |  | DATED
UNITS | 13 Residential Units + 1 ADU |  |  | ARCHITECTURAL |  | 2023-12-22
CITY | LOS ANGELES, CA 90038 |  |  | LANDSCAPE |  | 2023-09-12
SF | 10118.3 |  |  | 9900 SPEC |  | N/A
|  |  |  | OWNERS SPEC |  | N/A
|  | Total | 65137.2
|  | Total/Unit | 4652.6571
|  | $/SF | 6.4376
|  | Hrs/Unit | 91.0302
UNIT INTERIOR | [6 empty] | 18900
Units | 14 | 1350 |  |  |  |  | 18900
Add Alts
True Prime Coat | 14 | 250 |  |  |  |  | 3500
Eggshell Walls | 14 | 600 |  |  |  |  | 8400
Two Tone | 14 | 425 |  |  |  |  | 5950
Base over Floor | 14 | 90 |  |  |  |  | 1260
Cased Windows | 38 | 75 |  |  |  |  | 2850
Smooth Wall | 14 | 450 |  |  |  |  | 6300
CORRIDORS | [6 empty] | 10604.2
Wall SF | 6560 | 0.6 |  |  |  |  | 3936
Ceiling SF | 1358 | 0.4 |  |  |  |  | 543.2
Doors | 10 | 175 |  |  |  |  | 1750
Storage | 1 | 175 |  |  |  |  | 175
Base | 14 | 50 |  |  |  |  | 700
Entry Doors | 14 | 250 |  |  |  |  | 3500
Add Alts
True Prime Coat | 14 | 120 |  |  |  |  | 1680
Eggshell Walls | 14 | 200 |  |  |  |  | 2800
Two Tone | 14 | 135 |  |  |  |  | 1890
Smooth Wall | 14 | 125 |  |  |  |  | 1750
STAIRWELLS | [6 empty] | 15600
Stair 1 lvls | 6 | 1200 |  |  |  |  | 7200
Stair 2 lvls | 7 | 1200 |  |  |  |  | 8400
Add Alts
True Prime Coat | 13 | 120 |  |  |  |  | 1560
Eggshell Walls | 13 | 200 |  |  |  |  | 2600
Two Tone | 13 | 135 |  |  |  |  | 1755
Smooth Wall | 13 | 125 |  |  |  |  | 1625
Mask Hinges | 60 | 50 |  |  |  |  | 3000
AMENITY AREAS | [6 empty] | 5700
Rec Room | 2 | 2500 |  |  |  |  | 5000
Lobby | 1 | 700 |  |  |  |  | 700
EXTERIOR | [6 empty] | 12183
Door |  | 6 | 175 |  |  |  | 1050
Parapet |  | 329 | 2 |  |  |  | 658
Window Trim |  | 80 | 75 |  |  |  | 6000
Window Wood Verticals |  | 7 | 125 |  |  |  | 875
Balc Rail |  | 6 | 425 |  |  |  | 2550
Misc |  | 14 | 75 |  |  |  | 1050
Add Alts
Stucco Body |  | 10200 | 0.95 |  |  |  | 9690
Prime Stucco |  | 10200 | 0.5 |  |  |  | 5100
Stucco Accents at Balcs |  | 10 | 275 |  |  |  | 2750
Prime Stucco Accents at Balcs |  | 10 | 200 |  |  |  | 2000
Balc Doors |  | 5 | 250 |  |  |  | 1250
GARAGE | [6 empty] | 1800
Trash Room |  | 1 | 500 |  |  |  | 500
Doors |  | 4 | 200 |  |  |  | 800
Bike Storage Room |  | 1 | 500 |  |  |  | 500
Add Alts
Garage Walls |  | 3785 | 0.75 |  |  |  | 2838.75
Columns |  | 4 | 80 |  |  |  | 320
LANDSCAPE | [6 empty] | 350
Gates | 1 | 350 |  |  |  |  | 350
EXCLUSIONS
No 9900 Specifications available at time of bidding
No Owners Specifications available at time of bidding
0 VOC Paints and Systems
Scaffolding & Lifts
Saturday and Weekend Work
Water Proofing Membranes
ALL Exterior Caulking: Done by other
Power & Pressure washing
Masked Hinges
Paid Parking: Parking to be provided by Contractor